## Slide 1: AZNet II – Arizona Network
Steering Committee
January 25, 2013

## Slide 2: AZNet II – Arizona Network
Centurylink Update

## Slide 3: AZNet II – Arizona Network
Agenda
Opening Remarks
Operations Update
SLR Reporting
LAN Support Migration Project Update
CAaNES Vulnerability Assessment
Core/LAN Refresh Update
Closing Remarks

## Slide 4: AZNet II – Arizona Network
Chart: 
| August 2012 | September 2012 | October 2012 | November 2012 | December 2012
Created | 2964 | 2234 | 1945 | 1680 | 1445
Resolved/Closed | 1613 | 2175 | 2380 | 1633 | 1434
Cancelled | 167 | 152 | 117 | 55 | 40
Operations Update – Ticket counts

## Slide 5: AZNet II – Arizona Network
 | October |  |  |  |  |  |  | November |  |  |  |  |  |  | December |  |  |  |  |  | 
 | Sev 1 |  |  | Sev 2 |  |  |  | Sev 1 |  |  | Sev 2 |  |  |  | Sev 1 |  |  | Sev 2 |  |  | 
 | V | D | V/D | V | D | V/D | Total | V | D | V/D | V | D | V/D | Total | V | D | V/D | V | D | V/D | Total
Carrier | 2 | 1 | 2 | 5 | 8 |  | 18 |  |  |  | 6 | 8 | 2 | 16 |  | 1 | 3 | 1 | 12 |  | 17
Power |  | 1 |  | 1 | 3 |  | 5 |  |  |  | 1 | 2 |  | 3 |  |  | 1 | 1 | 3 |  | 5
Equipment |  | 1 |  | 7 | 5 |  | 13 | 6 |  |  | 7 | 1 |  | 14 | 1 |  | 1 | 12 | 5 |  | 19
Firewall/VPN |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  | 1 |  | 1
Customer |  |  |  | 3 | 7 |  | 10 |  |  |  | 3 | 6 |  | 9 |  |  |  |  | 2 |  | 2
Other |  |  |  |  | 1 |  | 1 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0
Operations Update – 4th Qtr Sev1/Sev2 Tickets

## Slide 6: AZNet II – Arizona Network
Chart: 
| Equipment | Firewall/VPN | Carrier | Power | Customer | Other
October | 13 | 0 | 18 | 5 | 10 | 1
November | 14 | 0 | 16 | 3 | 9 | 0
December | 19 | 1 | 17 | 5 | 2 | 0
Operations Update – 4th Qtr Sev1/Sev2 Tickets

## Slide 7: AZNet II – Arizona Network
SLR Reporting Summary
Current Status – SLR reporting is currently being designed. Discussions are being held to clear up any discrepancies in requirements and to come to a shared understanding of the reporting needs. SLR report data will be provided from Solarwinds & Remedy. Reports will initially be provided via SharePoint. Implementation of a reporting dashboard and ad-hoc reporting capabilities will follow.

## Slide 8: AZNet II – Arizona Network
SLR Reporting Plan
Action plan: (Target Date: 30 April 2013*)
  Finalize SLR discussions to clear up any discrepancies in requirements, come to a shared understanding of the reporting needs, and amend the contract to reflect any approved changes needed as an outcome of the discussions
  Design and implement Remedy MTTR tracking at the task level, along with field and value enhancements needed to identify SLRs per specific SLR requirements
  Design and implement Remedy SLR reports
  Design and implement Solarwinds SLR reports
  Design and implement reporting dashboard and ad-hoc reporting capabilities
  *Target Date is for final product; first two items will be completed in February; 3rd and 4th items will be completed early March
Notes: Finalize SLR discussions – 15 Feb
Design and implement Remedy MTTR tracking (dependent on SLR discussions) – 20 Feb
Design and implement Remedy SLR reports – 7 Mar (manual reports will be available earlier – as SLR items are finalized)
Design and implement Solarwinds reports – 7 Mar
Design and implement Reporting Dashboard and Ad-Hoc reporting capabilities (30 April)

## Slide 9: AZNet II – Arizona Network
 | Agency Totals |  |  |  |  | Survey Totals |  |  | 
 |  | Agencies without POC's | Total Surveys Sent | Total Agencies |  |  | Previous Week | Current Week | 
 | Totals | 35 | 90 | 125 |  | Total Agency Surveys Returned | 30 | 31 | 
 | *A1, A2, A4, A5, A6, A7, AD, AF, B1, B4, BD, BH, C1, C2, GV & IA have signed off. |  |  |  |  | *Total Surveys Ready for Sign Off | 17 | 8 | 
 |  |  |  |  |  | Agencies Out of Scope | 7 | 7 | 
 |  |  |  |  |  | Completed Agencies (Signed Off and under AZNet II Support) | 3 | 16 | 
LAN Support Migration Project Update

## Slide 10: AZNet II – Arizona Network
CAaNES Vulnerability Assessments
Meeting with CAaNES this week
Identify scanning intervals and frequency
  Fit within normal maintenance windows(monthly)
Indentify wave 1 of scanning and devices
  Segment out areas of the network
Finalize notification templates for agencies
  Finalize best method for transport of the scans

## Slide 11: AZNet II – Arizona Network
Core and Data Refresh updates
New core routers in hand and configuration work being done
Installation of Meet Me fiber into DC being scheduled
Racks and Power being added for new core items
Data refresh equipment being stocked
  Base refresh equipment is in CTL space in Phoenix
Standardizing configuration templates in process for refresh

## Slide 12: AZNet II – Arizona Network
Site Information and Survey
Finalizing refresh list
  Found some discrepancies between inventories; validation in process between lists
Site survey template being finalized; then communicated out to Agencies
Some examples on template are:
  Is the correct AC power source available; Equipment specs will be provided. Dedicated or shared power with proper grounding
  Does the location have Cat5 wiring or better. Cat5 is the min for transporting VoIP
  Does the MDF/IDF have the correct environmental for equipment specs
  Is there room in the current equipment closets for new equipment while old equipment is still in service

## Slide 13: AZNet II – Arizona Network
Closing Remarks