## Slide 1: Presentation to ITAC CH15002 CHG04
AZ DCS CHILDS Replacement Project
State of Arizona – Department of Child Safety
June 15, 2016

## Slide 2: Contents
Overview
Current Status
Today’s Change Request
Schedule
Costs
Risks
Communications and Outreach

## Slide 3: Overview
The Arizona Department of Child Safety (ADCS) is a human service organization dedicated to achieving safety, well-being and permanency for children, youth and families through leadership and the provision of quality services in partnership with communities.
In 1997, the CHildren’s Information Library and Data Source (CHILDS) was developed for the Arizona Department of Child, Youth, and Family Services to exchange information between various State and Federal information systems.
Through detailed analysis and evaluation of the current CHILDS system, ADCS has identified a list of key system shortfalls. These shortfalls include the following:
  Ineffective tools to support and drive ADCS business processes;
  Poor system usability and sustainability
  Deficient searching and matching functionality
ADCS has recently completed the first of a two-phased approach to procure, develop, and implement the replacement for CHILDS, known as Guardian.

## Slide 4: Current Status
ADCS recently completed a cost benefit analysis and feasibility study to ensure the selection of the most cost efficient and advantageous replacement solution.
  This solution will support the new Federal child welfare system requirements (CCWIS).
ADCS recently submitted the Implementation Advance Planning Document (IAPD) and received Federal approval on June 3, 2016.
  The Federal agency Administration for Children and Families (ACF) acknowledges that ADCS is at the vanguard of implementing a system that meets the CCWIS requirements.
  Approval includes Federal Match funding of up to $34M.
ADCS is pursuing a procurement strategy which:
  Starts with a mobile solution that will benefit case workers in the field (released June 9th, 2016);
  Next procure a foundational technology platform to enforce a consistent data model and data exchange standards;
  Followed by the functional modules, such as case management, financial management, provider management.

## Slide 5: Today’s Change Request
Pre-PIJ CH15002 included preparation and issuance of an RFP to hire a vendor to conduct a cost benefit analysis and feasibility study which was completed under a separate PIJ (CH15004).
Today’s Change Request (CHG04) is to extend the vendor engagement to include the following scope:
  Provide program coordination between State entities, such as ITAC, and Federal entities such as the Administration for Children and Families (ACF);
  Plan and participate in the procurement process;
  Create multiple RFPs and related documentation that align with the recommendations presented in the feasibility study (Pre-PIJ CH15004 deliverables);
  Maintain the Guardian roadmap/schedule.
To fulfill this scope, DCS is requesting $600,000 and an extended completion date of 12/31/16. This will allow DCS to issue all necessary RFPs for the Guardian program, at which point a new PIJ will be completed and this Pre-PIJ will be closed.

## Slide 6: Schedule
Provide your favorite schedule slide and talk about the plan
CHG04

## Slide 7: Costs
Pre-PIJ CH15002 included the work for DCS to procure vendor services to fulfill scope under Pre-PIJ CH15004, and for DCS to work with the vendor on this scope. The three change requests already approved for Pre-PIJ CH15002 include:
  Extend the end dates for Pre-PIJ CH15002 to ensure all Pre-PIJ CH15004 deliverables were clearly defined;
  Expand the scope of Pre-PIJ CH15002 for PCG to create the document required to report findings of the feasibility study to the Federal Government - Implementation Advance Planning Document (IAPD);
  Expand the scope of Pre-PIJ CH15002 for PCG to create an RFP for the mobile solution, and an RFP for the technology platform on which Guardian will be built.
Under Pre-PIJ CH15004, DCS hired PCG to conduct a feasibility study for the Guardian program (CHILDS Replacement). This scope included work for PCG to document the requirements necessary for the replacement system, and to conduct an alternatives analysis, cost benefit analysis, and feasibility study.
Fund Type | General Fund | Automation Projects Fund | Federal Funds | Total Costs
Current | $508,193 | - | $508,193 | $1,016,386
Requested | - | $300,000 | $300,000 | $600,000
 |  |  | Total Costs | $1,616,386
Fund Type | Automation Projects Fund | Federal Funds | Total Costs
Completed Costs | $308,499 | $308,499 | $616,998

## Slide 8: Risks
risk | mitigation
Executive Sponsorship Impact on agency organization, budget, effort | Reorganized Steering Committee to decide Specialized working groups to advise
Project Complexity Incremental benefit delivery requires coordination Data management between CHILDS and Guardian | IV&V vendor to maintain oversight and quality monitoring during the full span of the project Schedules with dependencies and contingency Coordination of CHILDS decommissioning
System Complexity Integration and configuration complexity | Concept of Operations Industry standards DCS oversight of vendors
Funding DCS and Federal budgets | Agreed funding to complete solution Buy-in from State, Federal, and DCS management
Competitive Procurement Limited vendor and evolving product market | Procurement strategy coordinated with RFP and evaluation criteria
System Acceptance Management need for reporting and analytics Changing DCS processes while configuring system Busy caseworkers with limited time for training | Business process redesign informs configuration Incremental delivery provides early successes, champions, and growing understanding Communication and training provides awareness

## Slide 9: Communications and Outreach
ADCS convened a steering committee during the feasibility study and will reconvene a revised steering committee as the initial RFPs are being evaluated.
ADCS is building a communications and outreach program to inform DCS management, staff, and providers on benefits and changes that the new system will bring about.
ADCS is maintaining status updates on the work with AZ state entities such as JLBC, ADOA, SPO; the Federal agency ACF; other states who are considering similar replacements for their child welfare systems; and a program of presentations through organizations such as APHSA.
ADCS will be pleased to update ITAC regularly as the project continues.

## Slide 10: Q&A